## Slide 1
LAURA B. JANUSEK
CHIEF PRODUCT OFFICER
MODERN TEACHER
@LBJANUSEK
#OSCON
GET YOUR
POKER FACE ON:
HOW TO USE PLANNING POKER TO SLAY PROJECT ESTIMATIONS

## Slide 2
PLANNING POKER:
What & Why
GET
REAL:
Examples from MT
LIVE ESTIMATIONS:
Planning Poker in Action!
WHAT ARE WE DOING HERE?
NEXT
STEPS:
Roadmapping our Road Trip
BE
SAASY:
Review of Online Tools
THAT’S A WRAP:
Q&A Time

## Slide 3
PLANNING POKER:
What & Why
GET
REAL:
Examples from MT
LIVE ESTIMATIONS:
Planning Poker in Action!
WHAT ARE WE DOING HERE?
NEXT
STEPS:
Roadmapping our Road Trip
BE
SAASY:
Review of Online Tools
THAT’S A WRAP:
Q&A Time

## Slide 4
#NoEstimates
Estimates can be too low
  Lots of techniques exist to improve accuracy
Estimates can be too high
  There are worse things
Estimates can be misused by management
  Management needs training
Estimates cut into dev time
  Not very much
Estimates are unnecessary – we should build whatever has the most value and then move on to the next
  Define value

## Slide 5
Planning Poker is a consensus-based estimation technique used by Agile teams globally.

## Slide 6
HISTORY
1948 – RAND Corporation formed, think tank that advises U.S. Armed Forces, later creates Delphi Method

## Slide 7
HISTORY
1948 – RAND Corporation formed, think tank that advises U.S. Armed Forces, later creates Delphi Method
1970s – Barry Boehm proposes “Wideband Delphi” method, popularized in Software Engineering Economics (1981)

## Slide 8
HISTORY
1948 – RAND Corporation formed, think tank that advises U.S. Armed Forces, later creates Delphi Method
1970s – Barry Boehm proposes “Wideband Delphi” method, popularized in Software Engineering Economics (1981)
2002 – Current form set out in article by James Grenning

## Slide 9
HISTORY
1948 – RAND Corporation formed, think tank that advises U.S. Armed Forces, later creates Delphi Method
1970s – Barry Boehm proposes “Wideband Delphi” method, popularized in Software Engineering Economics (1981)
2002 – Current form set out in article by James Grenning
2005 – Popularized by Mike Cohn’s “Agile Estimating and Planning”, trademarked by Mountain Goat Software

## Slide 10
HISTORY
1948 – RAND Corporation formed, think tank that advises U.S. Armed Forces, later creates Delphi Method
1970s – Barry Boehm proposes “Wideband Delphi” method, popularized in Software Engineering Economics (1981)
2002 – Current form set out in article by James Grenning
2005 – Popularized by Mike Cohn’s “Agile Estimating and Planning”, trademarked by Mountain Goat Software
Today – Variations used worldwide with a range of techniques & tools

## Slide 11
HOW IT WORKS

## Slide 12
HOW IT WORKS

## Slide 13
HOW IT WORKS

## Slide 14
HOW IT WORKS

## Slide 15
HOW IT WORKS

## Slide 16
HOW IT WORKS

## Slide 17
HOW IT WORKS

## Slide 18
HOW IT WORKS

## Slide 19
HOW IT WORKS

## Slide 20
HOW IT WORKS

## Slide 21
DISAGREEMENTS
HOW TO GET THE FINAL ESTIMATE
  Keep voting until everyone votes the same number
  Keep voting until estimates are “close enough” and average them
  Average the votes even if they’re not very close
  When averaging, keep exact average or round up

## Slide 22
DISAGREEMENTS
HOW TO GET THE FINAL ESTIMATE
NUMBER SEQUENCING
  Playing Cards:
    Ace, 2, 3, 4, 5, 6… King
  Modified Fibonacci:
    0, ½, 1, 3, 5, 8, 13, 20, 40, 100
  Sequential:
    0, ½, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 15…
  T-Shirt Sizes:
    xxs, xs, s, m, l, xl, xxl
  With Icons:
    Infinity means it can’t be done, coffee cup means I need a break
  And what do the numbers mean? Story points, ideal days, etc.

## Slide 23
DISAGREEMENTS
HOW TO GET THE FINAL ESTIMATE
NUMBER SEQUENCING
TO TIME OR NOT TO TIME
  Original purpose was to keep estimation meetings moving (Agile Alliance)
  Use a timer to limit each round?
  Use a timer to limit vote justifications?
  How long to set in both cases?

## Slide 24
DISAGREEMENTS
HOW TO GET THE FINAL ESTIMATE
NUMBER SEQUENCING
TO TIME OR NOT TO TIME
?

## Slide 25
BENEFITS
Promotes accuracy, prevents bias
Keeps things organized & moving
Can assist in task assignment
Allows for multiple timelines based on cuts

## Slide 26
PLANNING POKER:
What & Why
GET
REAL:
Examples from MT
LIVE ESTIMATIONS:
Planning Poker in Action!
WHAT ARE WE DOING HERE?
NEXT
STEPS:
Roadmapping our Road Trip
BE
SAASY:
Review of Online Tools
THAT’S A WRAP:
Q&A Time

## Slide 28
196
RAW MATH
6 Devs
5 days/week
30 points/week
196/30 = 6.4 weeks!

## Slide 30
196
RAW MATH = 6.4 weeks
VELOCITY
20 points/week
196/20 = 9.8 weeks!

## Slide 32
196
RAW MATH = 6.4 weeks
VELOCITY = 9.8 weeks
MAINTENANCE
3 points/week
Velocity = 17/week
196/17= 11.5 weeks!

## Slide 34
196
RAW MATH = 6.4 weeks
VELOCITY = 9.8 weeks
MAINTENANCE = 11.5 weeks
UNKNOWNS
35% increase!
196 * .35 = 67.55
196 + 67.55 = 263.55
263.55/17 = 15.5 weeks!

## Slide 36
196
RAW MATH = 6.4 weeks
VELOCITY = 9.8 weeks
MAINTENANCE = 11.5 weeks
UNKNOWNS = 15.5 weeks
DAYS OFF
Thanksgiving = 1 week
Vacations/Sick = 1 week
Total = 17.5 weeks

## Slide 38
196
RAW MATH = 6.4 weeks
VELOCITY = 9.8 weeks
MAINTENANCE = 11.5 weeks
UNKNOWNS = 15.5 weeks
DAYS OFF = 17.5 weeks
QUALITY ASSURANCE
Regression Testing & Cleanup = 1 week
Total = 18.5 weeks!

## Slide 40
PLAN FOR
HISTORICAL VELOCITY
MAINTENANCE
UNKNOWNS
DAYS OFF
QUALITY ASSURACE

## Slide 42
PLANNING POKER:
What & Why
GET
REAL:
Examples from MT
LIVE ESTIMATIONS:
Planning Poker in Action!
WHAT ARE WE DOING HERE?
NEXT
STEPS:
Roadmapping our Road Trip
BE
SAASY:
Review of Online Tools
THAT’S A WRAP:
Q&A Time

## Slide 44
Notes: Baltimore to Philadelphia – 2 hours

## Slide 45
Notes: Indianapolis to Nashville – 5 hours

## Slide 46
Notes: Green Bay WI to Traverse City MI
If drive around bottom – 8.5 hr
If drive around top – 6.5 hr
If take northern ferry – 6hr 15min

## Slide 47
bit.ly/osconpoker1

## Slide 48
Notes: Chicago to St Louis – 4h 41

## Slide 49
Notes: St Louis to Denver – 12h 14m

## Slide 50
Notes: Denver to El Paso – 9h 44m

## Slide 52
Notes: El Paso to Vegas – 10h 44m
Vegas to LA – 4h 9m

## Slide 55
PLANNING POKER:
What & Why
GET
REAL:
Examples from MT
LIVE ESTIMATIONS:
Planning Poker in Action!
WHAT ARE WE DOING HERE?
NEXT
STEPS:
Roadmapping our Road Trip
BE
SAASY:
Review of Online Tools
THAT’S A WRAP:
Q&A Time

## Slide 56
41 Hours
RAW MATH
24 hours in a day
41/24 = 1.7 days!

## Slide 58
41 Hours
RAW MATH = 1.7 days
VELOCITY
6 hours/day
41/6 = 6.8 days

## Slide 60
41 Hours
RAW MATH = 1.7 days
VELOCITY = 6.8 days
MAINTENANCE
Getting gas, bathroom breaks, etc. = 1 hour/day
41/5 = 8.2 days

## Slide 62
41 Hours
RAW MATH = 1.7 days
VELOCITY = 6.8 days
MAINTENANCE = 8.2 days
UNKNOWNS
Known Unknowns: Construction on the route
Unknown Unknowns: Flat tire, fender bender, etc.
Scope Creep: While we’re in the area…
30% increase!
41* .3 = 12.3
41+ 12.3 = 53.3
53.3/5 = 10.7 days!

## Slide 64
41 Hours
RAW MATH = 1.7 days
VELOCITY = 6.8 days
MAINTENANCE = 8.2 days
UNKNOWNS = 10.7 days
DAYS OFF
4th of July = push back start by 1 week!

## Slide 66
41 Hours
RAW MATH = 1.7 days
VELOCITY = 6.8 days
MAINTENANCE = 8.2 days
UNKNOWNS = 10.7 days
DAYS OFF = 17.7 days
QUALITY ASSURANCE
Must spend 1 day in each city on the route
6 cities = 6 days
Total = 23.7 days!

## Slide 68
PLAN FOR
HISTORICAL VELOCITY
MAINTENANCE
UNKNOWNS
DAYS OFF
QUALITY ASSURACE

## Slide 69
PLANNING POKER:
What & Why
GET
REAL:
Examples from MT
LIVE ESTIMATIONS:
Planning Poker in Action!
WHAT ARE WE DOING HERE?
NEXT
STEPS:
Roadmapping our Road Trip
BE
SAASY:
Review of Online Tools
THAT’S A WRAP:
Q&A Time

## Slide 70
HISTORY OF FINAL ESTIMATE
HISTORY OF INDIVIDUAL ESTIMATES
CUSTOM NUMBER SEQUENCE
CSV EXPORT
INTEGRATIONS
Notes: Very simple. No login or way to save
Can select from a few options for numbering
Can do multiple stories and see history of final estimates, but not of individual ones

## Slide 71
HISTORY OF FINAL ESTIMATE
HISTORY OF INDIVIDUAL ESTIMATES
CUSTOM NUMBER SEQUENCE
CSV EXPORT
INTEGRATIONS
Notes: Has some options for number sequences but can’t set own
Doesn’t create an average
No history of stories, just one at a time

## Slide 72
HISTORY OF FINAL ESTIMATE
HISTORY OF INDIVIDUAL ESTIMATES
CUSTOM NUMBER SEQUENCE
CSV EXPORT
INTEGRATIONS
Notes: Nice UI with history of all estimates
CSV export, but only shows average, not estimate of each player
Can create own number sequence
Can edit final estimate number instead of their auto round-up average

## Slide 73
HISTORY OF FINAL ESTIMATE
HISTORY OF INDIVIDUAL ESTIMATES
CUSTOM NUMBER SEQUENCE
CSV EXPORT
INTEGRATIONS
Notes: Can select from numbering options or create own
Can have multiple rooms with saved history
On card “flip”, gives bar graph of which estimates were most popular
Saves final estimate but not individuals
No CSV export, but website says has Jira integration

## Slide 74
HISTORY OF FINAL ESTIMATE
HISTORY OF INDIVIDUAL ESTIMATES
CUSTOM NUMBER SEQUENCE
CSV EXPORT
INTEGRATIONS
Notes: New, just in beta. No login or way to save?
Emphasizes integrations (Jira, Slack, Stride) but no CSV export. Also can be used as Jira plugin
Gives numbering options or can allow open votes of any number
Can see individual votes, but can’t see who voted them. Loses card flip feeling

## Slide 75
HISTORY OF FINAL ESTIMATE
HISTORY OF INDIVIDUAL ESTIMATES
CUSTOM NUMBER SEQUENCE
CSV EXPORT
INTEGRATIONS
Notes: Gives sequencing options but doesn’t let you set your own
Does CSV export of final estimates
More advanced features, like timer and hiding realtime votes, but I couldn’t get them to work

## Slide 76
HISTORY OF FINAL ESTIMATE
HISTORY OF INDIVIDUAL ESTIMATES
CUSTOM NUMBER SEQUENCE
CSV EXPORT
INTEGRATIONS
Notes: Lets you set points values
Does save history of individual estimates on each story
No way to export

## Slide 77
PLANNING POKER:
What & Why
GET
REAL:
Examples from MT
LIVE ESTIMATIONS:
Planning Poker in Action!
WHAT ARE WE DOING HERE?
NEXT
STEPS:
Roadmapping our Road Trip
BE
SAASY:
Review of Online Tools
THAT’S A WRAP:
Q&A Time

## Slide 78
LAURA B. JANUSEK
CHIEF PRODUCT OFFICER
MODERN TEACHER
@LBJANUSEK
#OSCON
THANK YOU!
GET YOUR POKER FACE ON:
HOW TO USE PLANNING POKER TO SLAY PROJECT ESTIMATIONS

## Slide 79
LAURA B. JANUSEK
CHIEF PRODUCT OFFICER
MODERN TEACHER
@LBJANUSEK
#OSCON
THANK YOU!
GET YOUR POKER FACE ON:
HOW TO USE PLANNING POKER TO SLAY PROJECT ESTIMATIONS
Session page on conference website
O’Reilly Events App